## Sheet1
Service | O365 Connection | Sync Job Status | Admin Portal Status | Modern Auth Approach | Modern Auth Limitations
SharePoint Online | Connect-PnPOnline -Url <string> -Credentials <Credentials> New-PnPSite New-PnPTenantSite Get-PnPSiteCollectionAdmin Get-PnPSite Get-PnPAuditing Get-PnPHubSite Get-PnPSubWebs Get-PnPGroup Set-PnPWeb Set-PnPTenantSite Set-PnPAuditing Add-PnPUserToGroup Add-PnPSiteCollectionAdmin | Dev Completed | Under Review | Use PnP with App ID and Certificate | Workflows will not be triggered (known issue) App needs to registered as Azure App as well as SharePoint App? To be confirmed with MS Test if connecting to PnPOnline will connect other sesssions automaticatlly. Certificate vs secret best practices
SharePoint Online | Connect-SPOService -Url <string> -Credential <Credentials> Set-SPOSite Set-SPOUser Get-SPOSite Get-SPODeletedSite |  | Under Review | Use PnP Online
Exchange Online | Connect-ExchangeOnline -Credential <Credentials> Get-UnifiedGroup Set-UnifiedGroup Add-UnifiedGroupLinks Remove-UnifiedGroupLinks |  | Under Review | Use PnP Online | Not able to provision groups with graph API and override Group Naming convention.
Azure AD | Connect-MsolService -Credential <Credentials> Get-MsolUser |  | Under Review | Try Connect-MsolService [-AdGraphAccessToken <String>] [-MsGraphAccessToken <String>] Use Graph API
MS Teams | Connect-MicrosoftTeams -Credential <Credentials> New-Team Get-TeamUser Add-TeamUser |  | Under Review | Try using alertnate PS Command with Access token and account ID Use Graph API | Not able to provision teams with graph API and override Group Naming convention.
Skype for Business Online | Import-Module SkypeOnlineConnector $cred = Get-Credential $sfbSession = New-CsOnlineSession –OverrideAdminDomain <string> -Credential $cred Import-PSSession $sfbSession -AllowClobber Grant-CsTeamsMeetingPolicy Grant-CsTeamsMessagingPolicy Grant-CsTeamsMeetingBroadcastPolicy Grant-CsTeamsAppPermissionPolicy Grant-CsTeamsAppSetupPolicy Grant-CsTeamsChannelsPolicy |  | Under Review |  | MS to provide alternative approach

## Sheet3
SPOService | PnPOnline | Description
Get-SPOSite | Get-PnPTenantSite | Returns one or more site collections
Get-SPODeletedSite | Get-PnPTenantRecycleBinItem | Returns all modern and classic site collections in the tenant scoped recycle bin
Get-SPODeletedSite -IncludeOnlyPersonalSite | N/A | Return all deleted site collections from the Recycle Bin including Personal Sites.
Exchange Online | PnPOnline | Description
Get-UnifiedGroup | Get-PnPUnifiedGroup | Returns detailed information about the Office 365 Group
Add-UnifiedGroupLinks | Add-PnPUserToGroup Set-PnPUnifiedGroup | Add members, owners to Office 365 groups Only members can be owners of a group, must first add a user as member before adding it as an owner.
Set-UnifiedGroup | N/A | Alternative approach: Using Graph API UnifiedGroupWelcomeMessageEnabled HiddenFromAddressListsEnabled HiddenFromExchangeClientsEnabled

## Sheet2
Enable single sign-on with O365 to run commands in user context

## Service-OAuth
Service | OAuth | Comments
MSOLService | Connect-MsolService [-AdGraphAccessToken <String>] [-MsGraphAccessToken <String>] | Not able to get connection using accesToken obtained by graph or PnP. Can't use a service principal to connect to AAD Alternative approach: Using Graph API to get o365 users
Exchange Online | N/A | Using Graph API or PnP to perform add users to O365 group/update group settings: hide from GAL/show in leftNav Outlook
MS Teams | Connect-MicrosoftTeams -TenantId <String> -CertificateThumbprint <String> -ApplicationId <String> | Alternative approach: Using Graph API to set private channel settings
SPO Service | N/A | Alternative approach: Using PnP with OAuth
PnP | Connect-PnPOnline -Url <String> -ClientId <String> -Tenant <String> -PEMCertificate <String> -PEMPrivateKey <String>